## Worksheet
PR Summary 2019
PURCHASE REQUEST
Date Received/Emailed | Purchase Request | Purpose | Enduse | PR No. | Requestor | WH Stocks | Item No. | Qty | Revised Qty | UOM | Grouping | Item Description | Status Remarks | Status | Date Needed | Remarks | End User's Comments
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 29 |  | bags | A | Cement, Portland - UNSERVED 4 bag |  | Partially Delivered | 2019-11-29 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 36 | Orig.: 36.00 lengths | lengths | D | Bar, Steel, Deformed/Corrugated, 10mm | 11.20.2019 - Delivered DR# 1055-CNPR | Fully Delivered | 2019-11-29 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 6 | Orig.: 6.00 m? Rev. 1: 6.00 m? | m? | A | Gravel, 3/4 - UNSERVED 1.68 m³ |  | Cancelled | 2019-11-29 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 40 | Orig.: 40.00 pcs. | pcs. | A | Block, Hallow, Concrete, 4" x 8" x 16" | 11.28.2019 - Delivered DR# 1071-CNPR 12.03.2019 - Delivered DR# 1114-CNPR | Fully Delivered | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 3 | Orig.: 3.00 m? Rev. 1: 3.00 m? | m? | A | Sand, Mixing | 11.26.2019 - Delivered DR# 1070-CNPR | Fully Delivered | 2019-11-29 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 13 |  | sheets | H | Board, Hardiflex, 1/4" x 4' x 8' | 12.03.2019 - Delivered DR# 1107-CNPR 12.19.2019 - Delivered DR# 1162-CNPR | Fully Delivered | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 24 |  | lengths | S | Purlins, C, 2" x 3" x 6m x 0.1 | Superseded by PR No:SPE19-1146, with changes in quantity from 24 lengths to 9 lengths. 11.26.19 | Cancelled | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 4 |  | pcs. | H | Door, Flush, 80cm x 210cm | Canvassing Ongoing | Pending | 2019-11-22 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 1 |  | pc. | H | Door, UPVC, Flush, 60cm x 210cm | Canvassing Ongoing | Pending | 2019-11-22 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 1 | Orig.: 1.00 set | set | H | Door, Jamb, 2"x 4" | 12.03.2019 - Delivered DR# 1107-CNPR | Fully Delivered | 2019-11-22 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 5 | Orig.: 5.00 sets | sets | U | Door Knob | 12.20.2019 - Delivered DR# 1173-CNPR | Fully Delivered | 2019-11-29 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 10 |  | lengths | R | Bar, Angle, 1/4" x 1-1/2" x 1-1/2" x 6m | AOQ Done - For TE | Pending | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 2 | Orig.: 2.00 sets | sets | Y | Frame, Jalousie Window, High, 1m | 12.19.2019 - Delivered DR# 1149-CNPR | Fully Delivered | 2019-11-22 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 22 | Orig.: 22.00 pcs. | pcs. | Y | Jalousie, Glass, Smoke Type, Long, 55cm Thick | 12.19.2019 - Delivered DR# 1149-CNPR | Fully Delivered | 2019-11-22 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 5 |  | lengths | R | Purlins, C, 1.0 mm, 2" x 3" x 6m | Cancelled item - same item on item # 7 11.19.19 | Cancelled | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 7 | Orig.: 3.00 sheets Rev. 1: 3.00 sheets | sheets | N | Plywood, Marine, 3/4" x 4' x 8' - UNSERVED 1 sheets |  | Partially Delivered | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 7 |  | lengths | M | Lumber, S4S, 1" x 4" x 6' | For RFQ | Pending | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 10 |  | lengths | M | Lumber, S4S, 1" x 2" x 8' | For RFQ | Pending | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 46 | Orig.: 46.00 pcs. | pcs. | BW | Chair, Stool, Monoblock, Plastic - UNSERVED 16 pcs. |  | Partially Delivered | 2019-11-29 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 2 |  | rolls | I | Insulator, Tarp Foil, Roof, 1 Meter Width - UNSERVED 1 rolls |  | Partially Delivered | 2019-11-22 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 3 | Orig.: 3.00 gals. | gals. | A | Rugby, Contact Cement | 12.16.2019 - Delivered DR# 1151-CNPR | Fully Delivered | 2019-11-22 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 140 | Orig.: 88.00 pcs. | pcs. | V | Tiles, Floor, 8" x 8" - UNSERVED 52 pcs. |  | Partially Delivered | 2019-11-22 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 33 |  | pcs. | V | Tiles, Floor, 12" x 12" | Change in specs. Will PO 88 pcs. only for 20 cm x 30 cm. 01.07.20 | Cancelled | 2019-11-22 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 55 |  | pcs. | V | Tiles, Wall, 8" X 8" | Change in specs. Will PO 88 pcs. only for 20 cm x 30 cm. 01.07.20 | Cancelled | 2019-11-22 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 17 |  | pcs. | V | Tiles, Wall, 12" x 12" | Change in specs. Will PO 88 pcs. only for 20 cm x 30 cm. 01.07.20 | Cancelled | 2019-11-22 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 1 | Orig.: 1.00 set | set | H | Toilet Bowl, w/ Tank & Cover | 12.03.2019 - Delivered DR# 1108-CNPR | Fully Delivered | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 2 |  | pcs. | H | Holder, Toilet Paper | Cancelled by End user via Phone call, reflected on email thread as of 11.28.19 11.28.19 | Cancelled | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 2 | Orig.: 2.00 sets Rev. 1: 2.00 sets | sets | H | Basin, Hand, w/ Complete Fittings (P-trap and Faucets) | 12.20.2019 - Delivered DR# 1178-CNPR | Fully Delivered | 2019-11-22 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 9 | Orig.: 9.00 lengths Rev. 1: 9.00 lengths | lengths | X | Tile Trim | 01.16.2020 - Delivered DR# 1242-CNPR | Fully Delivered | 2019-11-22 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 5 | Orig.: 5.00 pcs. | pcs. | H | Elbow, PVC, 90 degrees, 1/2" | 12.03.2019 - Delivered DR# 1107-CNPR | Fully Delivered | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 2 | Orig.: 2.00 pcs. | pcs. | H | Adaptor, Female, PVC, 1/2" | 12.03.2019 - Delivered DR# 1107-CNPR | Fully Delivered | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 6 | Orig.: 6.00 pcs. | pcs. | H | Elbow, PVC, 90 deg, 4" | End user advised to cancel item#s: 3, 5 and 6 c/o Ms. Joy Bating via Hang out. Thus, created new Purchase Order to supersede under # PSPE19-1065-1119 11.28.19 | Cancelled | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 5 | Orig.: 5.00 pcs. | pcs. | H | Tee, Reducer, PVC, 4" x 2" | End user advised to cancel item#s: 3, 5 and 6 c/o Ms. Joy Bating via Hang out. Thus, created new Purchase Order to supersede under # PSPE19-1065-1119 11.28.19 | Cancelled | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 4 | Orig.: 4.00 pcs. | pcs. | H | Strainer, Floor, Stainless Steel, 2? | 12.03.2019 - Delivered DR# 1107-CNPR | Fully Delivered | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 3 | Orig.: 3.00 pcs. | pcs. | H | Water Faucet, Brass | 12.03.2019 - Delivered DR# 1108-CNPR | Fully Delivered | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 1 | Orig.: 1.00 pc. | pc. | H | Valve, Ball, PVC, 1/2" | 12.03.2019 - Delivered DR# 1107-CNPR | Fully Delivered | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 1 |  | set | P | Fire Hose Reel Cabinet, Mild Steel/Stainless Steel w/ Fire Hose Reel, 1" x 30m, Complete Accessories, 150 psi, Size of Cabinet: 750mmx 750mmx 250mm | For RFQ | Pending | 2019-11-29 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 3 |  | tanks | AP | Fire extinguisher, 10 lbs, ABC Chemical - UNSERVED 1 tanks |  | Partially Delivered | 2019-11-29 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 4 | Orig.: 4.00 lengths Rev. 1: 4.00 lengths | lengths | R | Pipe, Black Iron 2" diameter, Schedule 40 | 02.04.2020 - Delivered DR# 1293-CNPR | Fully Delivered | 2019-11-29 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 3 |  | lengths | R | Pipe, Black Iron, 1-1/4" diameter, Schedule 40 | For PO - AOQ Done (awarded) | Pending | 2019-11-29 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 10 |  | pcs. | Q | Elbow, Black Iron, Schedule 40, 2" x 90 deg. - UNSERVED 4 pcs. |  | Partially Delivered | 2019-11-29 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 5 |  | pcs. | Q | Elbow, Black Iron, Schedule 40, 1-1/4" x 90 | AOQ Done - For TE | Pending | 2019-11-29 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 10 |  | pcs. | Q | Flange, Black Iron, 2" | 01.31.2020 - Delivered DR# 1282-CNPR | Fully Delivered | 2019-11-29 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 2 |  | lengths | C | Bar, Angle, 1/4" x 1" x 1" x 6m | 11.29.2019 - Delivered DR# 1095-CNPR | Fully Delivered | 2019-11-29 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 1 |  | gal. | O | Paint, Primer, Epoxy, Gray | 02.07.2020 - Delivered DR# 1300-CNPR | Fully Delivered | 2019-11-29 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 1 |  | gal. | AA | Thinner, Lacquer |  | Fully Delivered | 2019-11-29 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 5 |  | pcs. | F | Brush, Paint, 2" | 12.19.2019 - Delivered DR# 1155-CNPR | Fully Delivered | 2019-11-29 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 1 |  | gal. | O | Epoxy, Top Coat, Red | 02.06.2020 - Delivered DR# 1295-CNPR | Fully Delivered | 2019-11-29 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 0 |  | cyl. | Z | Acetylene | Processed manually because of System error dated 11/13/19 ; AM, with PO No: FR-168-5001 delivered to site as of 11.14.19 under DR#4931 11.18.19 | Cancelled | 2019-11-29 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 0 |  | cyls. | C | Oxygen | Processed manually because of System error dated 11/13/19 ; AM, with PO No: FR-168-5002 delivered to site as of 11.14.19 under DR#4932 11.18.19 | Cancelled | 2019-11-29 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 1 |  | roll | K | Tape, PTFE, Industrial, 3/4", (Teflon) | 02.06.2020 - Delivered DR# 1281-CNPR | Fully Delivered | 2019-11-29 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 10 |  | pcs. | F | Brush, Roller, 4", with Handle | 12.19.2019 - Delivered DR# 1155-CNPR | Fully Delivered | 2019-11-29 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 0 |  | pcs. | H | Disc, Cutting, 4" | Processed manually because of System error dated 11/13/19 ; AM, with PO No: FR-168-5003 delivered to site as of 11.14.19 under DR#4933 11.18.19 | Cancelled | 2019-11-29 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 5 |  | kgs. | W | Nail, Common, 2-1/2" | 12.09.2019 - Delivered DR# 1125-CNPR | Fully Delivered | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 2 |  | kgs. | H | Nail, Common, 1" | Canvassing Ongoing | Pending | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 15 |  | kgs. | C | Tie Wire, #16 | 11.29.2019 - Delivered DR# 1097-CNPR 12.19.2019 - Delivered DR# 1165-CNPR | Fully Delivered | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 5 |  | kgs. | E | Electrode, Welding, 1/8" x E6011 | Cancelled PO. Item Not needed for the project. 06.01.20 | Cancelled | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 10 |  | kgs. | D | Electrode, Welding, 1/8" x E6013 | For RFQ | Pending | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 5 |  | pcs. | H | Disc, Grinding, 4" x 1/4" x 5/8" | Canvassing Ongoing | Pending | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 2 |  | pcs. | A | Disc, Cutting, Diamond, 4" - UNSERVED 1 pcs. |  | Partially Delivered | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 20 |  | pairs | K | Gloves, Working, Ma-ong | 12.09.2019 - Delivered DR# 1109-CNPR | Fully Delivered | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 1 |  | gal. | T | Sealant, Roof, (Vulcaseal) | 12.16.2019 - Delivered DR# 1148-CNPR | Fully Delivered | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 2 |  | kgs. | H | Compound, Grout, Tile | AOQ Done - For TE | Pending | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 2 |  | bags | H | Adhesive, Tile | AOQ Done - For TE | Pending | 2019-11-15 | FR-168-2019
2019-04-04 | Bacolod | Construction of CENPRI Canteen | CENPRI Employees | SPE19-1065-CNPR | Iris J. Sixto/Irish Dawn E. Torres | 0 |  | 10 |  | pcs. | G | Drill Bit, Metal, 1/8" | 11.22.2019 - Delivered DR# 1064-CNPR | Fully Delivered | 2019-11-15 | FR-168-2019