## Worksheet
JOR Summary 2021
JOB ORDER REQUEST
On Hold | Proceed | Date Received/Emailed | Delivery Date | Completion Date | JO Request | Project Title | JO No. | Requestor | Qty | Revised Qty | UOM | Grouping | Scope of Work | Materials Offer | Materials QTY | Materials UOM | Status Remarks | Status | Remarks | Cancel Remarks | End User's Comments
|  | 2021-09-08 | 2021-09-08 | 2021-09-11 | CNPR-S | INSTALLATION OF ADDITIONAL CCTV CAMERA IN DRAIN CANALS AND LADIES DORM | JOR 2021-1-CNPR / CNPR-S-EMG-9821-1002 | GODFREY SAMANO | 5 |  | lot/s | A | Materials & Equipment preparations. |  |  |  | For JO - AOQ Done (awarded) | Pending
|  | 2021-09-08 | 2021-09-08 | 2021-09-11 | CNPR-S | INSTALLATION OF ADDITIONAL CCTV CAMERA IN DRAIN CANALS AND LADIES DORM | JOR 2021-1-CNPR / CNPR-S-EMG-9821-1002 | GODFREY SAMANO | 10 |  | pc/s | A | Lay-out & excavation of underground pathway |  |  |  | For JO - AOQ Done (awarded) | Pending
|  | 2021-09-08 | 2021-09-08 | 2021-09-11 | CNPR-S | INSTALLATION OF ADDITIONAL CCTV CAMERA IN DRAIN CANALS AND LADIES DORM | JOR 2021-1-CNPR / CNPR-S-EMG-9821-1002 | GODFREY SAMANO | 2 |  | pc/s | B | Excavation of pole foundation |  |  |  | For RFQ | Pending
|  | 2021-09-08 | 2021-09-08 | 2021-09-11 | CNPR-S | INSTALLATION OF ADDITIONAL CCTV CAMERA IN DRAIN CANALS AND LADIES DORM | JOR 2021-1-CNPR / CNPR-S-EMG-9821-1002 | GODFREY SAMANO | 20 |  | pc/s | C | Erection of steel pole | Testing lng danay ah | 0 |  |  | JO Issued
|  | 2021-09-08 | 2021-09-08 | 2021-09-11 | CNPR-S | INSTALLATION OF ADDITIONAL CCTV CAMERA IN DRAIN CANALS AND LADIES DORM | JOR 2021-1-CNPR / CNPR-S-EMG-9821-1002 | GODFREY SAMANO | 5 |  | pc/s | C | Assistance in cable pulling & laying of conduit pipe | Testing lng danay ah | 0 |  |  | JO Issued
|  | 2021-09-08 | 2021-09-08 | 2021-09-11 | CNPR-S | INSTALLATION OF ADDITIONAL CCTV CAMERA IN DRAIN CANALS AND LADIES DORM | JOR 2021-1-CNPR / CNPR-S-EMG-9821-1002 | GODFREY SAMANO | 3 |  | pc/s | C | Backfilling & compaction | Testing lng danay ah | 0 |  |  | JO Issued
|  | 2021-09-08 | 2021-09-08 | 2021-09-11 | CNPR-S | INSTALLATION OF ADDITIONAL CCTV CAMERA IN DRAIN CANALS AND LADIES DORM | JOR 2021-1-CNPR / CNPR-S-EMG-9821-1002 | GODFREY SAMANO | 5 |  | pc/s |  | Hauling of materials & housekeeping |  |  |  | For RFQ | Pending
|  | 2021-09-08 | 2021-09-08 | 2021-09-11 | CNPR-S | INSTALLATION OF ADDITIONAL CCTV CAMERA IN DRAIN CANALS AND LADIES DORM | JOR 2021-1-CNPR / CNPR-S-EMG-9821-1002 | GODFREY SAMANO | 3 |  | lot/s |  | Accomplish the attached Excavation Specification |  |  |  | For RFQ | Pending