## Worksheet
JOR Summary 2021
JOB ORDER REQUEST
On Hold | Proceed | Date Received/Emailed | Delivery Date | Completion Date | JO Request | Project Title | JO No. | Requestor | Qty | Revised Qty | UOM | Grouping | Scope of Work | Status Remarks | Status | Remarks | Cancel Remarks | End User's Comments
|  | 2021-05-05 | 2021-05-05 | 2021-05-30 | admin | sample purpose | JOR 2021-1-CNPR | sample request | 30 |  | pc/s | A | item testing 1 | 05.11.2021 - Delivered DR# 1016-CNPR 05.05.2021 - Delivered DR# 1002-CNPR 05.12.2021 - Delivered DR# 1003-CNPR 05.11.2021 - Delivered DR# 1004-CNPR 05.05.2021 - Delivered DR# 1005-CNPR 05.05.2021 - Delivered DR# 1006-CNPR 05.12.2021 - Delivered DR# 1015-CNPR 05.12.2021 - Delivered DR# 1017-CNPR 05.13.2021 - Delivered DR# 1018-CNPR 05.11.2021 - Delivered DR# 1019-CNPR 05.11.2021 - Delivered DR# 1020-CNPR 05.11.2021 - Delivered DR# 1021-CNPR 05.11.2021 - Delivered DR# 1022-CNPR 05.11.2021 - Delivered DR# 1023-CNPR | Fully Delivered
| ✓ | 2021-05-05 | 2021-05-05 | 2021-05-30 | admin | sample purpose | JOR 2021-1-CNPR | sample request | 50 |  | pc/s |  | item testing 2 | For RFQ | Pending
|  | 2021-05-05 | 2021-05-05 | 2021-05-30 | admin | sample purpose | JOR 2021-1-CNPR | sample request | 10 |  | pc/s |  | item testing 3 | For RFQ | Pending
| ✓ | 2021-05-05 | 2021-05-05 | 2021-05-30 | admin | sample purpose | JOR 2021-2-CNPR | sample request | 30 |  | pc/s |  | item testing 1 | For RFQ | Pending
|  | 2021-05-05 | 2021-05-05 | 2021-05-30 | admin | sample purpose | JOR 2021-2-CNPR | sample request | 50 |  | pc/s |  | item testing 2 | For RFQ | Pending
|  | 2021-05-05 | 2021-05-05 | 2021-05-30 | admin | sample purpose | JOR 2021-2-CNPR | sample request | 10 |  | pc/s |  | item testing 3 | For RFQ | Pending
|  | 2021-05-06 | 2021-05-06 | 2021-05-10 | ADMIN | TESTING JOR PURPOSE | JOR 2021-3-CNPR | TESTING JOR REQUEST BY | 120 | Orig.: 90.00 PC/S | PC/S | A | TESTING ITEM 1 | 05.11.2021 - Delivered DR# 1024-CNPR (20.00 PC/S) 05.11.2021 - Delivered DR# 1025-CNPR (10.00 PC/S) 05.19.2021 - Delivered DR# 1031-CNPR (90.00 PC/S) | Partially Delivered
|  | 2021-05-06 | 2021-05-06 | 2021-05-10 | ADMIN | TESTING JOR PURPOSE | JOR 2021-3-CNPR | TESTING JOR REQUEST BY | 30 |  | PC/S | B | TESTING ITEM 2
|  | 2021-05-06 | 2021-05-06 | 2021-05-10 | ADMIN | TESTING JOR PURPOSE | JOR 2021-3-CNPR | TESTING JOR REQUEST BY | 50 | Orig.: 45.00 PC/S | PC/S |  | TESTING ITEM 3
|  | 2021-03-18 | 2021-05-25 | 2021-05-25 | Bacolod Office |  | JO2024-29-CNPR | IT Office Renovation | 10 |  | lots | B | Sample only |  | JO Issued (10.00 lots)
|  | 2021-06-06 | 2021-06-02 | 2021-06-02 | Bacolod | Retrofitting | CENJO-EM029-369-CNPR | Bago Site ter | 10 |  |  | M | TEST 1 |  | JO Issued (10.00 )
|  | 2021-06-06 | 2021-06-02 | 2021-06-02 | Bacolod | Retrofitting | CENJO-EM029-369-CNPR | Bago Site ter | 5 |  |  | C | TEST 2 | Canvassing Ongoing | Pending
|  | 2021-06-06 | 2021-06-02 | 2021-06-02 | Bacolod | Retrofitting | CENJO-EM029-369-CNPR | Bago Site ter | 5 |  |  | P | TEST 3 | Canvassing Ongoing | Pending
|  | 2021-06-06 | 2021-06-03 | 2021-06-03 | Bacolod | Retrofitting | CENJO9-369-CNPR | Bago Site ter | 10 |  |  | J | TEST 1 | ambot 06.03.21 | Cancelled
|  | 2021-06-06 | 2021-06-03 | 2021-06-03 | Bacolod | Retrofitting | CENJO9-369-CNPR | Bago Site ter | 5 | Orig.: 3.00 Rev. 1: 3.00 |  | O | TEST 2 | 06.03.2021 - Delivered DR# 1043-CNPR 06.09.2021 - Delivered DR# 1049-CNPR | Fully Delivered
|  | 2021-06-06 | 2021-06-03 | 2021-06-03 | Bacolod | Retrofitting | CENJO9-369-CNPR | Bago Site ter | 5 |  |  | G | TEST 3 | ambot 06.03.21 | Cancelled |  | asd
|  | 2021-06-06 | 2021-06-03 | 2021-06-03 | Bacolod | Printing of tarpaulin for Environmental Compliance Certificate (ECC) notice as per DENR-EMB Compliance | CENJO-PUR-1001-CNPR | Bago Site | 10 |  |  | E | Provide labor, materials & services for the following scope of work: 1. Printing of tarpaulin, size 3 ft. x 5 ft. for ECC Notice compliance to DENR-EMB. Note: see attached drawing. Material: Tarpaulin
|  | 2021-06-06 | 2021-06-03 | 2021-06-03 | Bacolod | Printing of tarpaulin for Environmental Compliance Certificate (ECC) notice as per DENR-EMB Compliance | CENJO-PUR-1001-CNPR | Bago Site | 5 |  |  | P | There are many variations of passages of Lorem Ipsum available | 06.10.2021 - Delivered DR# 1047-CNPR | Fully Delivered
|  | 2021-06-06 | 2021-06-03 | 2021-06-03 | Bacolod | Printing of tarpaulin for Environmental Compliance Certificate (ECC) notice as per DENR-EMB Compliance | CENJO-PUR-1001-CNPR | Bago Site | 5 |  |  | P | The standard Lorem Ipsum passage, used since the 1500s | ambot 06.03.21 | Cancelled
|  | 2021-06-10 | 2021-06-04 | 2021-06-04 | Bacolod | Printing of tarpaulin for Environmental Compliance Certificate (ECC) notice as per DENR-EMB Compliance | CENJO-ITB-12002-CNPR | Bago Site | 10 |  |  | M | Sample 1 | For JO - AOQ Done (awarded) | Pending
|  | 2021-06-10 | 2021-06-04 | 2021-06-04 | Bacolod | Printing of tarpaulin for Environmental Compliance Certificate (ECC) notice as per DENR-EMB Compliance | CENJO-ITB-12002-CNPR | Bago Site | 5 |  |  | P | Sample 2 | 06.04.2021 - Delivered DR# 1050-CNPR 06.05.2021 - Delivered DR# 1051-CNPR | Fully Delivered
| ✓ | 2021-06-10 | 2021-06-04 | 2021-06-04 | Bacolod | Printing of tarpaulin for Environmental Compliance Certificate (ECC) notice as per DENR-EMB Compliance | CENJO-ITB-12002-CNPR | Bago Site | 5 |  |  | R | Sample 3 | Canvassing Ongoing | Pending |  | zsfzdfds