## Worksheet
PR Summary 2021
PURCHASE REQUEST
On Hold | Proceed | Date Received/Emailed | Purchase Request | Purpose | Enduse | PR No. | Requestor | WH Stocks | Item No. | Qty | Revised Qty | UOM | Grouping | Item Description | Verified Date Needed | Estimated | Status Remarks | Status | Date Needed | Remarks | Cancel Remarks | End User's Comments
|  | 2021-08-27 |  | Installation of Jacket Water Injector Cooling By-Pass Line | DG Unit 4 and Unit 5 | MAI21-1877-CNPR | Ruel Beato | 2 | 1 | 1 |  | length | A | BI Pipe, Sched 40, 1 1/2" NPS |  |  | 10.09.2021 - Delivered DR# 3500-CNPR | Fully Delivered | Sep 11, 2021 | MAI-266-2021
|  | 2021-08-27 |  | Installation of Jacket Water Injector Cooling By-Pass Line | DG Unit 4 and Unit 5 | MAI21-1877-CNPR | Ruel Beato | 0 | 2 | 2 |  | lengths | A | BI Pipe, Sched 40, 1" NPS |  |  | 10.09.2021 - Delivered DR# 3500-CNPR | Fully Delivered | Sep 11, 2021 | MAI-266-2021
|  | 2021-08-27 |  | Installation of Jacket Water Injector Cooling By-Pass Line | DG Unit 4 and Unit 5 | MAI21-1877-CNPR | Ruel Beato | 0 | 3 | 1 |  | pc | C | Gate Valve, 150 lbs rating, Rising Stem, Flange Type, Cast Steel, 1 1/2" |  |  | 12.13.2021 - Delivered DR# 3921-CNPR | Fully Delivered | Sep 11, 2021 | MAI-266-2021
|  | 2021-08-27 |  | Installation of Jacket Water Injector Cooling By-Pass Line | DG Unit 4 and Unit 5 | MAI21-1877-CNPR | Ruel Beato | 0 | 4 | 3 |  | pcs | C | Gate Valve, 150 lbs rating, Rising Stem, Flange Type, Cast Steel, 1" |  |  | 12.13.2021 - Delivered DR# 3921-CNPR | Fully Delivered | Sep 11, 2021 | MAI-266-2021
|  | 2021-08-27 |  | Installation of Jacket Water Injector Cooling By-Pass Line | DG Unit 4 and Unit 5 | MAI21-1877-CNPR | Ruel Beato | 0 | 5 | 3 |  | pcs | C | B.I. Elbow, Long Radius, Seamless, Buttweld End, Schedule 40, 1 1/2" x 90° |  |  |  | PO Issued | Sep 11, 2021 | MAI-266-2021
|  | 2021-08-27 |  | Installation of Jacket Water Injector Cooling By-Pass Line | DG Unit 4 and Unit 5 | MAI21-1877-CNPR | Ruel Beato | 0 | 6 | 8 |  | pcs | C | B.I. Elbow, Long Radius, Seamless, Buttweld End, Schedule 40, 1" x 90° |  |  | 12.13.2021 - Delivered DR# 3921-CNPR | Fully Delivered | Sep 11, 2021 | MAI-266-2021
|  | 2021-08-27 |  | Installation of Jacket Water Injector Cooling By-Pass Line | DG Unit 4 and Unit 5 | MAI21-1877-CNPR | Ruel Beato | 0 | 7 | 4 |  | pcs | C | Slip-on Flange, Class 150, ANSI B16.5, Raised Faced, 1 1/2" |  |  | 12.13.2021 - Delivered DR# 3921-CNPR | Fully Delivered | Sep 11, 2021 | MAI-266-2021
|  | 2021-08-27 |  | Installation of Jacket Water Injector Cooling By-Pass Line | DG Unit 4 and Unit 5 | MAI21-1877-CNPR | Ruel Beato | 0 | 8 | 10 |  | pcs | C | Slip-on Flange, Class 150, ANSI B16.5, Raised Faced, 1" |  |  | 12.13.2021 - Delivered DR# 3921-CNPR | Fully Delivered | Sep 11, 2021 | MAI-266-2021
|  | 2021-08-27 |  | Installation of Jacket Water Injector Cooling By-Pass Line | DG Unit 4 and Unit 5 | MAI21-1877-CNPR | Ruel Beato | 0 | 9 | 16 |  | sets | B | Hex Head Bolt, High Tensile, Full-thread, Grade 5, M14 x 45 mm x 1.5 Pitch, with Nut & Lock Washer |  |  | 10.04.2021 - Delivered DR# 3531-CNPR | Fully Delivered | Sep 11, 2021 | MAI-266-2021
|  | 2021-08-27 |  | Installation of Jacket Water Injector Cooling By-Pass Line | DG Unit 4 and Unit 5 | MAI21-1877-CNPR | Ruel Beato | 0 | 10 | 40 |  | sets | B | Hex Head Bolt, High Tensile, Full-thread, Grade 5, M12 x 45 mm x 1.5 Pitch, with Nut & Lock Washer |  |  | 10.04.2021 - Delivered DR# 3531-CNPR | Fully Delivered | Sep 11, 2021 | MAI-266-2021
|  | 2021-08-27 |  | Installation of Jacket Water Injector Cooling By-Pass Line | DG Unit 4 and Unit 5 | MAI21-1877-CNPR | Ruel Beato | 0 | 11 | 4 |  | pcs | B | U-bolt, 1/4" x 1 1/2" NPS, w/ Nut & Lock Washer |  |  | 10.04.2021 - Delivered DR# 3531-CNPR | Fully Delivered | Sep 11, 2021 | MAI-266-2021
|  | 2021-08-27 |  | Installation of Jacket Water Injector Cooling By-Pass Line | DG Unit 4 and Unit 5 | MAI21-1877-CNPR | Ruel Beato | 0 | 12 | 10 |  | pcs | B | U-bolt, 3/8" x 1" NPS, w/ Nut & Lock Washer |  |  | 10.04.2021 - Delivered DR# 3531-CNPR | Fully Delivered | Sep 11, 2021 | MAI-266-2021