## Worksheet
PR Summary 2021
PURCHASE REQUEST
Date Received/Emailed | Purchase Request | Purpose | Enduse | PR No. | Requestor | WH Stocks | Item No. | Qty | Revised Qty | UOM | Grouping | Item Description | Status Remarks | Status | Date Needed | Remarks | End User's Comments
2021-01-04 |  | Additional Materials for Ladies Dorm | CENPRI Female Employees | SPE21-1530-CNPR | Iris Sixto | 0 |  | 150 | Orig.: 150.00 pcs | pcs | A | Screw Metal, 3/16 dia x 2" | 01.06.2021 - Delivered DR# 2254-CNPR | Fully Delivered | 2021-01-04 | FR-004-2021
2021-01-06 | Manila/Bacolod | Construction of Ladies Dorm Additional Materials | Ladies Dorm | SPE21-1531-CNPR | Iris J. Sixto | 0 |  | 1 |  | cu,mtr | A | 3/4 gravel | 01.09.2021 - Delivered DR# 2268-CNPR | Fully Delivered | 2021-01-06 | FR-004-2021
2021-01-06 | Manila/Bacolod | Construction of Ladies Dorm Additional Materials | Ladies Dorm | SPE21-1531-CNPR | Iris J. Sixto | 0 |  | 150 |  | pcs |  | metal screw, flat head, 3/16x2"long | item already served superseded by PR#: SPE21-1530-CNPR with PO#: PSPE21-1530-2330-CNPR 01.06.21 | Cancelled | 2021-01-06 | FR-004-2021
2021-01-06 | Manila/Bacolod | Construction of Ladies Dorm Additional Materials | Ladies Dorm | SPE21-1531-CNPR | Iris J. Sixto | 0 |  | 3 |  | cu,mtr | A | mixing sand | 01.09.2021 - Delivered DR# 2268-CNPR | Fully Delivered | 2021-01-06 | FR-004-2021
2021-01-08 |  | Additional materilas for Ladies Dormitory | CENPRI Female Employees | SPE21-1532-CNPR |  | 0 |  | 2 |  | yards | A | Chrome pipe, 3/4" | 01.11.2021 - Delivered DR# 2280-CNPR | Fully Delivered | 2021-01-08
2021-01-08 |  | Additional materilas for Ladies Dormitory | CENPRI Female Employees | SPE21-1532-CNPR |  | 0 |  | 2 |  | pcs | A | End post, 3/4" | 01.11.2021 - Delivered DR# 2280-CNPR | Fully Delivered | 2021-01-08
2021-01-04 | Manila/Bacolod | Double Wall & Ceiling | Ladies Dorm | SPE21-1533-CNPR | Iris J. Sixto | 0 |  | 105 | Orig.: 105.00 sheets | sheets | A | Fiber cement board 4'x8'x4.5mm thk | 01.19.2021 - Delivered DR# 2289-CNPR | Fully Delivered | 2021-01-08 | FR-003-2021
2021-01-04 | Manila/Bacolod | Double Wall & Ceiling | Ladies Dorm | SPE21-1533-CNPR | Iris J. Sixto | 0 |  | 300 |  | lenght | A | Metal stud 50X75X0.5mm thk | 01.21.2021 - Delivered DR# 2284-CNPR | Fully Delivered | 2021-01-08 | FR-003-2021
2021-01-04 | Manila/Bacolod | Double Wall & Ceiling | Ladies Dorm | SPE21-1533-CNPR | Iris J. Sixto | 0 |  | 28 |  | lenght | A | Double furring channel 50x19x0.6mm thk | 01.21.2021 - Delivered DR# 2284-CNPR | Fully Delivered | 2021-01-08 | FR-003-2021
2021-01-04 | Manila/Bacolod | Double Wall & Ceiling | Ladies Dorm | SPE21-1533-CNPR | Iris J. Sixto | 0 |  | 24 |  | lenght | A | Carrying channel 38x12x0.75mm thk | 01.21.2021 - Delivered DR# 2284-CNPR | Fully Delivered | 2021-01-08 | FR-003-2021
2021-01-04 | Manila/Bacolod | Double Wall & Ceiling | Ladies Dorm | SPE21-1533-CNPR | Iris J. Sixto | 11 |  | 10 |  | box | A | Blind rivets 1/8"x1/2" | 01.13.2021 - Delivered DR# 2290-CNPR | Fully Delivered | 2021-01-08 | FR-003-2021
2021-01-04 | Manila/Bacolod | Double Wall & Ceiling | Ladies Dorm | SPE21-1533-CNPR | Iris J. Sixto | 10 |  | 10 |  | pcs | A | Drill bit 1/8" | 01.21.2021 - Delivered DR# 2284-CNPR | Fully Delivered | 2021-01-08 | FR-003-2021
2021-01-04 | Manila/Bacolod | Double Wall & Ceiling | Ladies Dorm | SPE21-1533-CNPR | Iris J. Sixto | 0 |  | 300 |  | pcs | A | W-clip/ metal furring clip | 01.13.2021 - Delivered DR# 2290-CNPR | Fully Delivered | 2021-01-08 | FR-003-2021
2021-01-04 | Manila/Bacolod | Double Wall & Ceiling | Ladies Dorm | SPE21-1533-CNPR | Iris J. Sixto | 62 |  | 5 |  | kgs | A | Welding rod E6011 | Canvassing Ongoing | Pending | 2021-01-08 | FR-003-2021
2021-01-04 | Manila/Bacolod | Double Wall & Ceiling | Ladies Dorm | SPE21-1533-CNPR | Iris J. Sixto | 1 |  | 2 |  | pcs | A | Aviation snips/furring scissors | 01.12.2021 - Delivered DR# 2286-CNPR | Fully Delivered | 2021-01-08 | FR-003-2021
2021-01-28 | Manila/Bacolod | Painting of Powerhouse Steel Flooring Platform(Additional consumables) | Special Projects/Operation | SPE/Operation21-1534-CNPR | Iris J. Sixto | 0 |  | 10 |  | gls | A | Thinner, Acrylic | 01.19.2021 - Delivered DR# 2297-CNPR | Fully Delivered | 2021-01-14 | FR-001-2021
2021-01-28 | Manila/Bacolod | Painting of Powerhouse Steel Flooring Platform(Additional consumables) | Special Projects/Operation | SPE/Operation21-1534-CNPR | Iris J. Sixto | 0 |  | 5 | Orig.: 5.00 gls Rev. 1: 5.00 gls | gls | D | Epoxy enamel paint (green) | 02.05.2021 - Delivered DR# 2364-CNPR | Fully Delivered | 2021-01-14 | FR-001-2021
2021-01-28 | Manila/Bacolod | Painting of Powerhouse Steel Flooring Platform(Additional consumables) | Special Projects/Operation | SPE/Operation21-1534-CNPR | Iris J. Sixto | 0 |  | 5 |  | gls | B | Epoxy primer paint (Gray) | 01.19.2021 - Delivered DR# 2298-CNPR | Fully Delivered | 2021-01-14 | FR-001-2021
2021-01-28 | Manila/Bacolod | Painting of Powerhouse Steel Flooring Platform(Additional consumables) | Special Projects/Operation | SPE/Operation21-1534-CNPR | Iris J. Sixto | 0 |  | 10 |  | pcs | C | Brush,Paint,Roller,Refill,4" | 01.18.2021 - Delivered DR# 2296-CNPR | Fully Delivered | 2021-01-14 | FR-001-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 0 |  | 1 |  | pail |  | Multicleaner, Uniliq, Water Based | For RFQ | Pending | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 21 |  | 20 |  | liters | K | Diesel Oil | 01.26.2021 - Delivered DR# 2325-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 55 |  | 20 |  | liters | K | Kerosene | 01.26.2021 - Delivered DR# 2325-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 13 |  | 3 |  | cans | A | Penetrant, Multi Use, WD-40, Net Content: 382 mL / 311G / 12.9 FL.OZ | 01.20.2021 - Delivered DR# 2310-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 0 |  | 1 |  | can | B | Polish, Metal, A-1 Premium Grade Net Content, 150ml | 01.21.2021 - Delivered DR# 2311-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 0 |  | 1 |  | cyl | L | Acetylene | 02.03.2021 - Delivered DR# 2328-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 4 |  | 2 |  | cyls | M | Oxygen |  | PO Issued (2.00 cyls) | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 57 |  | 10 |  | kgs | CK | Electrode, Welding, E6011, 1/8" x 12" |  | PO Issued (10.00 kgs) | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 57 |  | 10 |  | kgs | PL | Electrode, Welding, E6013, 1/8" x 12" |  | PO Issued (10.00 kgs) | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 1 |  | 1 |  | kg | G | Electrode, Welding, E304, 3/32" x 12" (Stainless Steel Welding Electrode) | 01.22.2021 - Delivered DR# 2320-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 0 |  | 1 |  | pair | B | Gloves, Welding, 16" - 18" long | 01.21.2021 - Delivered DR# 2311-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 4 |  | 1 |  | pcs | B | Glass, Clear, 2" x 4" | 01.21.2021 - Delivered DR# 2311-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 6 |  | 2 |  | pcs | B | Glass, Dark , #10 | 01.21.2021 - Delivered DR# 2311-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 0 |  | 1 | Orig.: 1.00 pc | pc | XC | Grinding Wheel, Gray, 6x1x3/4" |  | PO Issued (1.00 pc) | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 0 |  | 1 | Orig.: 1.00 pc | pc | XC | Circular Brush, 6", Preferred Brand: Creston |  | PO Issued (1.00 pc) | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 95 |  | 25 |  | pcs | CK | Disc, Cutting, 4" x 3/32" x 5/8" (Tyrolit 41 A30Q-BF) |  | PO Issued (25.00 pcs) | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 26 |  | 5 |  | sheets |  | Paper, Abrasive, Grit 1000 - Creston Silicon Carbide Abrasive Paper | For RFQ | Pending | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 3 |  | 10 |  | sheets | C | Paper, Abrasive, Grit 800 - Creston Silicon Carbide Abrasive Paper | 01.22.2021 - Delivered DR# 2312-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 42 |  | 10 | Orig.: 10.00 sheets | sheets | XC | Paper, Abrasive, Grit 600 - Creston Silicon Carbide Abrasive Paper |  | PO Issued (10.00 sheets) | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 24 |  | 10 |  | sheets | EZ | Paper, Abrasive, Grit 120 - Creston Silicon Carbide Abrasive Paper | 02.06.2021 - Delivered DR# 2389-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 18 |  | 2 | Orig.: 2.00 pcs | pcs | CL | Brush, Steel | 02.05.2021 - Delivered DR# 2401-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 4 |  | 2 | Orig.: 2.00 pcs | pcs | BX | Blade, Hacksaw, HSS, 300mm/12", 18 TPI | 02.05.2021 - Delivered DR# 2400-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 0 |  | 1 |  | pc | H | Drill Bit, HSS, 1/4" | 01.22.2021 - Delivered DR# 2323-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 0 |  | 3 |  | pcs | H | Drill Bit, HSS, 1/8" | 01.22.2021 - Delivered DR# 2323-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 0 |  | 2 | Orig.: 2.00 pcs | pcs | H | Drill Bit, HSS, 1/16" | 01.22.2021 - Delivered DR# 2322-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 1 |  | 1 |  | bottle | B | Adhesive, Rugby, Contact Cement, 300mL | 01.21.2021 - Delivered DR# 2311-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 3 |  | 1 |  | pc | J | Gasket Maker, Red RTV, High Temperature (up to 650 °F), 85 Grams | 01.22.2021 - Delivered DR# 2319-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 0 |  | 2 |  | pcs | E | Bulb, LED, Daylight, 14 Watts, Input Voltage: AC 180-265V 50/60 Hz | 01.22.2021 - Delivered DR# 2318-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 0 |  | 6 |  | pcs | D | Battery, AA, 1.5 Volts | 01.21.2021 - Delivered DR# 2313-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 0 |  | 4 |  | pcs | D | Battery, AAA, 1.5Volts | 01.21.2021 - Delivered DR# 2313-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 54 |  | 10 |  | kgs | AW | Rags, Cotton | 02.08.2021 - Delivered DR# 2393-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 25 |  | 25 |  | pairs | C | Gloves, Knitted Cotton | 01.22.2021 - Delivered DR# 2312-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 4 |  | 10 |  | pcs | C | Chalkstone | 01.22.2021 - Delivered DR# 2312-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 5 |  | 2 |  | pcs | C | Brush, Paint, 2" | 01.22.2021 - Delivered DR# 2312-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 1 |  | 2 |  | gallons | F | Soap, Liquid, Industrial | 01.21.2021 - Delivered DR# 2315-CNPR | Fully Delivered | 2021-01-18 | PR-008-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1537-CNPR | Alona T. Arroyo | 10 |  | 10 |  | pcs |  | Bag, Garbage, Large | For RFQ | Pending | 2021-01-18 | PR-008-2021
2021-01-20 | Bacolod | Turbocharger Overhauling Training in 5days (Jan 25-29,2021) | Godfrey Samano, Edwin Bejec, Exequil Corino | HAS21-1539-CNPR | Ricky D. Madeja/Analyn Sulig | 0 |  | 10 | Orig.: 1.00 pcs | pcs | A | Size: XL Disposable PPE includes suit and mask made by micro fiber that is water repellant and auto clave, double flap zepper to lessen chances of droplets from getting in with shoe cover minimal stiches to reduce contamination risk. | opted to tailored PPE 01.22.21 | Cancelled | 2021-01-21 | HR-015-2021
2021-01-20 | Bacolod | Turbocharger Overhauling Training in 5days (Jan 25-29,2021) | Godfrey Samano, Edwin Bejec, Exequil Corino | HAS21-1539-CNPR | Ricky D. Madeja/Analyn Sulig | 0 |  | 5 |  | pcs | B | Size: XXXL Disposable PPE includes suit and mask made by micro fiber that is water repellant and auto clave, double flap zepper to lessen chances of droplets from getting in with shoe cover minimal stiches to reduce contamination risk. | For RFQ | Pending | 2021-01-21 | HR-015-2021
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 13 |  | 1 |  | can |  | WD40 Multi-purpose, 382ml | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 0 |  | 2 |  | cans |  | Contact cleaner, 360ml | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 24 |  | 5 |  | rolls |  | Vinyl electrical tape (Big), brand: armak | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 0 |  | 50 |  | pcs. |  | Cable tie 450mm x 5mm | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 0 |  | 100 |  | pcs. |  | Cable tie100mm x 3mm | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 0 |  | 100 |  | pcs. |  | Cable tie 150mm x 4mm | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 5 |  | 10 |  | pairs |  | Electrical cotton with rubber gloves | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 25 |  | 5 |  | pairs |  | Cotton gloves | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 0 |  | 2 |  | pcs. |  | Rechargeable battery AA, 1500 mAH | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 1 |  | 1 |  | pc |  | Battery 9 volts | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 0 |  | 3 |  | rolls |  | Masking tape 1/4" | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 3 |  | 2 |  | rolls |  | Masking tape 1/2" | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 5 |  | 2 |  | rolls |  | Masking tape 1" | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 0 |  | 2 |  | cartridge |  | Brady wire marker tape Part Number: M21-750-595-YL | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 1 |  | 1 |  | gal. |  | Denatured alcohol, 1 gal./3L | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 6 |  | 4 |  | quarts |  | Distilled water | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 5 |  | 5 |  | pcs. |  | Abrasive paper 180, water resistant | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 0 |  | 20 |  | pcs. |  | Insulated terminal lugs Size: 16-14 AWG, Fork type | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 0 |  | 20 |  | pcs. |  | Insulated terminal lugs Size: 12-10 AWG, Fork type | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 4 |  | 1 |  | piece |  | Broom (Baguio/Ordinary thick) | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 0 |  | 2 |  | pieces |  | Drill bit, 1/4 | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 1 |  | 2 |  | pieces |  | Drill bit, 1/8 | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 18 |  | 3 |  | pieces |  | Paint brush, 1" | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-13 | 44207 | EIC | UOM | Kennah Sasamoto21-1540-CNPR | 1 | 18 |  | 3 |  | pcs. |  | Steel brush | Re upload new PR EIC21-1541-CNPR 01.21.21 | Cancelled | 2021-01-21
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 54 |  | 5 |  | kgs. | A | Cotton rags | 01.28.2021 - Delivered DR# 2329-CNPR | Fully Delivered | 2021-01-18 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 13 |  | 1 |  | can | B | WD40 Multi-purpose, 382ml | 01.28.2021 - Delivered DR# 2339-CNPR | Fully Delivered | 2021-01-21 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 0 |  | 2 |  | cans | H | Contact cleaner, 360ml | For RFQ | Pending | 2021-01-21 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 24 |  | 5 |  | rolls | C | Vinyl electrical tape (Big), brand: armak | 01.28.2021 - Delivered DR# 2330-CNPR | Fully Delivered | 2021-01-21 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 0 |  | 50 |  | pcs. | O | Cable tie 450mm x 5mm | 02.05.2021 - Delivered DR# 2359-CNPR | Fully Delivered | 2021-01-21 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 0 |  | 100 | Orig.: 100.00 pcs. | pcs. | O | Cable tie100mm x 3mm |  | PO Issued (100.00 pcs.) | 2021-01-21 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 0 |  | 100 |  | pcs. | N | Cable tie 150mm x 4mm - UNSERVED 99 pack |  | Partially Delivered | 2021-01-21 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 5 |  | 10 |  | pairs | D | Electrical cotton with rubber gloves | 01.28.2021 - Delivered DR# 2344-CNPR | Fully Delivered | 2021-01-21 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 25 |  | 5 |  | pairs | E | Cotton gloves | 01.28.2021 - Delivered DR# 2331-CNPR | Fully Delivered | 2021-01-21 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 0 |  | 2 |  | pcs. | F | Rechargeable battery AA, 1500 mAH | 01.28.2021 - Delivered DR# 2332-CNPR | Fully Delivered | 2021-01-21 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 1 |  | 1 |  | pc | F | Battery 9 volts | 01.28.2021 - Delivered DR# 2332-CNPR | Fully Delivered | 2021-01-21 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 0 |  | 3 |  | rolls | M | Masking tape 1/4" | 01.28.2021 - Delivered DR# 2342-CNPR | Fully Delivered | 2021-01-21 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 3 |  | 2 |  | rolls | G | Masking tape 1/2" | 01.28.2021 - Delivered DR# 2333-CNPR | Fully Delivered | 2021-01-21 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 5 |  | 2 |  | rolls | G | Masking tape 1" | 01.28.2021 - Delivered DR# 2333-CNPR | Fully Delivered | 2021-01-21 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 0 |  | 2 |  | cartridge |  | Brady wire marker tape Part Number: M21-750-595-YL | For RFQ | Pending | 2021-01-21 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 1 |  | 1 |  | gal. | H | Denatured alcohol, 1 gal./3L | 01.28.2021 - Delivered DR# 2334-CNPR | Fully Delivered | 2021-01-21 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 6 |  | 4 |  | quarts | I | Distilled water | 01.28.2021 - Delivered DR# 2336-CNPR | Fully Delivered | 2021-01-21 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 5 |  | 5 |  | pcs. | H | Abrasive paper 180, water resistant | 01.28.2021 - Delivered DR# 2334-CNPR | Fully Delivered | 2021-01-21 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 0 |  | 20 |  | pcs. | O | Insulated terminal lugs Size: 16-14 AWG, Fork type | For PO - AOQ Done (awarded) | Pending | 2021-01-21 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 0 |  | 20 | Orig.: 20.00 pcs. | pcs. | O | Insulated terminal lugs Size: 12-10 AWG, Fork type |  | PO Issued (20.00 pcs.) | 2021-01-21 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 4 |  | 1 |  | piece | J | Broom (Baguio/Ordinary thick) |  | PO Issued (1.00 piece) | 2021-01-21 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 0 |  | 2 |  | pieces | L | Drill bit, 1/4 | 01.28.2021 - Delivered DR# 2340-CNPR | Fully Delivered | 2021-01-21 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 1 |  | 2 |  | pieces | L | Drill bit, 1/8 | 01.28.2021 - Delivered DR# 2340-CNPR | Fully Delivered | 2021-01-21 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 18 |  | 3 |  | pieces | H | Paint brush, 1" | 01.28.2021 - Delivered DR# 2334-CNPR | Fully Delivered | 2021-01-21 | PR-009-2021
2021-01-11 | Manila/Bacolod | EIC Consumables | EIC | EIC21-1541-CNPR | Kennah Sasamoto | 18 |  | 3 |  | pcs. | K | Steel brush | 01.28.2021 - Delivered DR# 2337-CNPR | Fully Delivered | 2021-01-21 | PR-009-2021
2021-01-20 | Bacolod | Turbocharger Overhauling Training (Jan. 25-29, 2021) ( 5 days) |  | HAS21-1542-CNPR | Ricky D. Madeja | 0 |  | 12 |  | yards | A | Cloth; Micro Fiber, Color: Gray | End use of the PR not indicated 01.25.21 | Cancelled | 2021-01-22 | HR-015-2021
2021-01-23 | Bacolod | For Commercial Operation | CENPRI | FLM21-1543-CNPR | Fleur de liz Ambong | 0 |  | 4000 |  | liters | A | Diesel |  | PO Issued (4000.00 liters) | 2021-01-25
2021-01-20 | Bacolod | PPE for Turbocharger Overhauling Training in 5days (Jan 25-29,2021) | Godfrey Samano | HAS21-1544-CNPR | Ricky D. Madeja/Analyn Sulig | 0 |  | 12 |  | yards | A | Cloth; Micro Fiber, Color: Gray | 01.22.2021 - Delivered DR# 2349-CNPR | Fully Delivered | 2021-01-25
2021-01-25 | Bacolod | For Commercial Operation | CENPRI | FLM21-1545-CNPR | Fleur de liz Ambong | 0 |  | 80000 |  | liters | A | Bunker C Fuel Oil |  | PO Issued (80000.00 liters) | 2021-01-27
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 85 |  | bags |  | Cement, Portland | For RFQ | Pending | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 8 |  | cu. mtrs | A | Washed sand |  | PO Issued (8.00 cu. mtrs) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 16 |  | cu. mtrs | A | Gravel 3/4 |  | PO Issued (16.00 cu. mtrs) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 5 |  | kgs | B | Nail, Common, 4" | 02.08.2021 - Delivered DR# 2367-CNPR | Fully Delivered | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 3 | Orig.: 3.00 kgs | kgs | M | Nail, Common, 2" |  | PO Issued (3.00 kgs) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 3 |  | kgs | B | Nail, Common, 1-1/2" | 02.08.2021 - Delivered DR# 2367-CNPR | Fully Delivered | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 2 | Orig.: 2.00 sheet Rev. 1: 2.00 sheet | sheet | M | Ordinary plywood 4'x8'x1/2" thk. |  | PO Issued (2.00 sheet) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 30 |  | length | M | Good lumber 2"x2"x8'(prefer Gmelina tree) |  | PO Issued (30.00 length) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 15 |  | m | M | Hose level 3/8" |  | PO Issued (15.00 m) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 10 |  | lgths | M | Pipe, GI, Sch 40, 4" dia. x 20' long |  | PO Issued (10.00 lgths) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 23 | Orig.: 23.00 lgths Rev. 1: 23.00 lgths | lgths | CG | Angle bar 1" x 1" x 3/16"Thk. x 6m |  | PO Issued (23.00 lgths) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 15 | Orig.: 15.00 lgths Rev. 1: 15.00 lgths | lgths | M | Deformed steel bar 10mmx6m long, Gr.33 |  | PO Issued (15.00 lgths) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 72 | Orig.: 72.00 lgths Rev. 1: 72.00 lgths | lgths | J | C-Purlins 2" x 4" x 1.2mm thk x 6m long |  |  | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 1 | Orig.: 1.00 sheet Rev. 1: 1.00 sheet | sheet | M | MS plate 4' x 8' x 12mm thk |  | PO Issued (1.00 sheet) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 120 |  | pcs | GP | Bolt 3/8 x 1 1/4" long,high tensile,full thread w/ nut & washer |  | PO Issued (120.00 pcs) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 80 |  | pcs | GP | Bolt 12mm x 60mm long,high tensile,full thread w/ nut & washer |  | PO Issued (80.00 pcs) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 6 |  | cylinder | DV | Acetylene |  | PO Issued (6.00 cylinder) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 3 |  | cylinder | HR | Oxygen |  | PO Issued (3.00 cylinder) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 4 |  | pcs | KX | Carbide bits 6mmx10mm |  | PO Issued (2.00 pcs) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 4 |  | boxes | M | Electrodes, Welding, 1/8" x E6011 |  | PO Issued (4.00 boxes) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 2 | Orig.: 2.00 box | box | M | Electrodes, Welding, 1/8" x E6013 |  | PO Issued (2.00 box) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 2 |  | units | K | Welding Rod Handle, 300amp heavy duty | 02.06.2021 - Delivered DR# 2376-CNPR | Fully Delivered | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 5 |  | pcs | C | Glass, Lens, Dark, #10 | 02.08.2021 - Delivered DR# 2368-CNPR | Fully Delivered | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 5 |  | pcs | C | Glass, Clear | 02.08.2021 - Delivered DR# 2368-CNPR | Fully Delivered | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 10 |  | pcs | D | Brush, Steel |  | PO Issued (10.00 pcs) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 5 |  | kgs | E | Rags, Cotton |  | PO Issued (5.00 kgs) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 10 |  | pcs | C | Disc, Cutting, 4" | 02.08.2021 - Delivered DR# 2368-CNPR | Fully Delivered | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 15 |  | pcs | F | Grinding disc 4" | 02.08.2021 - Delivered DR# 2370-CNPR | Fully Delivered | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 3 |  | pcs | C | Cutting disc 14" | 02.08.2021 - Delivered DR# 2368-CNPR | Fully Delivered | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 20 |  | sets | F | Gloves, Cotton | 02.08.2021 - Delivered DR# 2370-CNPR | Fully Delivered | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 3 | Orig.: 3.00 boxes | boxes | M | Screw, Self-Drilling, 8mm x 2", (Tek Screw) |  | PO Issued (3.00 boxes) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 2 |  | pcs |  | Magnet Socket, 8mm | For RFQ | Pending | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 37 |  | shts | M | Sheet, GI, Corrugated, 12ft x 80cm x guage 0.4 |  | PO Issued (37.00 shts) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 37 |  | shts | M | Sheet, GI, Corrugated, 10ft x 80cm x guage 0.4 |  | PO Issued (37.00 shts) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 8 |  | shts | M | Ridge, Roof | AOQ Done - For TE 01.01.70 | Pending | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 10 | Orig.: 10.00 gals | gals | N | Primer, Metal, Red Oxide |  | PO Issued (10.00 gals) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 5 |  | gals | O | Roofguard, Color: Green, Brand: Boysen |  | PO Issued (5.00 gals) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 1 |  | ltr | FA | Sealant, Roof, Brand: Vulcaseal |  | PO Issued (1.00 ltr) | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 4 |  | gals | G | Lacquer Thinner, Paint | For RFQ | Pending | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 2 |  | pcs | F | Brush, Roller, W/ Handle, 4'' | 02.08.2021 - Delivered DR# 2370-CNPR | Fully Delivered | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 5 |  | pcs | F | Brush, Roller, Refill, 4" | 02.08.2021 - Delivered DR# 2370-CNPR | Fully Delivered | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 4 |  | pcs | F | Brush, Paint, 2" | 02.08.2021 - Delivered DR# 2370-CNPR | Fully Delivered | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 2 |  | pcs | G | Brush, Paint, 4" | 02.08.2021 - Delivered DR# 2371-CNPR | Fully Delivered | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 5 |  | pcs | G | Drill Bit, Metal, 1/8 | 02.08.2021 - Delivered DR# 2371-CNPR | Fully Delivered | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 1 |  | box | K | Rivets, Blind, Aluminum, 1/8" x 3/4" | 02.06.2021 - Delivered DR# 2376-CNPR | Fully Delivered | 2021-02-01 | SPE-023-2021
2021-01-14 | Manila/Bacolod | Construction of Generator Storage Building - Phase 1 | Generator Storage Building | SPE / OPE21-1546-CNPR | Iris Sixto | 0 |  | 10 |  | shts | G | Sandpaper, G80 | 02.08.2021 - Delivered DR# 2371-CNPR | Fully Delivered | 2021-02-01 | SPE-023-2021
2021-01-19 | Bacolod | For PPE's used during Transaction COMECQ Area (Power House Area) | HSES | HAS21-1547-CNPR | Ricky D. Madeja/Analyn Sulig | 0 |  | 100 | Orig.: 100.00 yards | yards | A | Cloth; Micro Fiber, Color: Grey |  | PO Issued (96.00 yards) | 2021-02-02
2021-02-02 | Manila/Bacolod | Painting of Ladies Dorm | Ladies Dorm | SPE21-1548-CNPR | Iris J. Sixto | 0 |  | 20 | Orig.: 10.00 gls Rev. 1: 10.00 gls Rev. 2: 10.00 gls | gls | F | Enamel, Semi Gloss, Blue Rays |  | PO Issued (10.00 gls) | 2021-02-02 | SPE-022-2021
2021-02-02 | Manila/Bacolod | Painting of Ladies Dorm | Ladies Dorm | SPE21-1548-CNPR | Iris J. Sixto | 0 |  | 20 | Orig.: 10.00 gls Rev. 1: 10.00 gls Rev. 2: 10.00 gls | gls | F | Latex, Flat White |  | PO Issued (10.00 gls) | 2021-02-02 | SPE-022-2021
2021-02-02 | Manila/Bacolod | Painting of Ladies Dorm | Ladies Dorm | SPE21-1548-CNPR | Iris J. Sixto | 0 |  | 25 |  | gls | F | Latex, Semi gloss,Off-White |  | PO Issued (10.00 gls) | 2021-02-02 | SPE-022-2021
2021-02-02 | Manila/Bacolod | Painting of Ladies Dorm | Ladies Dorm | SPE21-1548-CNPR | Iris J. Sixto | 0 |  | 10 | Orig.: 5.00 gls Rev. 1: 5.00 gls Rev. 2: 5.00 gls | gls | F | Enamel,Semi Gloss,Off-White |  | PO Issued (5.00 gls) | 2021-02-02 | SPE-022-2021
2021-02-02 | Manila/Bacolod | Painting of Ladies Dorm | Ladies Dorm | SPE21-1548-CNPR | Iris J. Sixto | 0 |  | 2 |  | bags | F | Skim Coat Putty |  | PO Issued (1.00 bags) | 2021-02-02 | SPE-022-2021
2021-02-02 | Manila/Bacolod | Painting of Ladies Dorm | Ladies Dorm | SPE21-1548-CNPR | Iris J. Sixto | 0 |  | 1 | Orig.: 1.00 gal Rev. 1: 1.00 gal Rev. 2: 1.00 gal | gal | F | Wood Filler |  | PO Issued (1.00 gal) | 2021-02-02 | SPE-022-2021
2021-02-02 | Manila/Bacolod | Painting of Ladies Dorm | Ladies Dorm | SPE21-1548-CNPR | Iris J. Sixto | 0 |  | 1 | Orig.: 1.00 gal Rev. 1: 1.00 gal Rev. 2: 1.00 gal | gal | F | Enamel, Semi Gloss, Chocolait Brown |  | PO Issued (1.00 gal) | 2021-02-02 | SPE-022-2021
2021-02-02 | Manila/Bacolod | Painting of Ladies Dorm | Ladies Dorm | SPE21-1548-CNPR | Iris J. Sixto | 0 |  | 3 |  | gls | A | Paint thinner | 02.06.2021 - Delivered DR# 2383-CNPR | Fully Delivered | 2021-02-02 | SPE-022-2021
2021-02-02 | Manila/Bacolod | Painting of Ladies Dorm | Ladies Dorm | SPE21-1548-CNPR | Iris J. Sixto | 0 |  | 1 | Orig.: 1.00 gal Rev. 1: 1.00 gal Rev. 2: 1.00 gal | gal | F | Sanding Sealer |  | PO Issued (1.00 gal) | 2021-02-02 | SPE-022-2021
2021-02-02 | Manila/Bacolod | Painting of Ladies Dorm | Ladies Dorm | SPE21-1548-CNPR | Iris J. Sixto | 0 |  | 5 |  | gls | E | Lacquer Thinner | 02.06.2021 - Delivered DR# 2384-CNPR | Fully Delivered | 2021-02-02 | SPE-022-2021
2021-02-02 | Manila/Bacolod | Painting of Ladies Dorm | Ladies Dorm | SPE21-1548-CNPR | Iris J. Sixto | 0 |  | 4 |  | gls | F | lacquer Flo |  | PO Issued (2.00 gls) | 2021-02-02 | SPE-022-2021
2021-02-02 | Manila/Bacolod | Painting of Ladies Dorm | Ladies Dorm | SPE21-1548-CNPR | Iris J. Sixto | 0 |  | 1 | Orig.: 1.00 gal Rev. 1: 1.00 gal Rev. 2: 1.00 gal | gal | F | Wood Stain,Dark Wall Nut |  | PO Issued (1.00 gal) | 2021-02-02 | SPE-022-2021
2021-02-02 | Manila/Bacolod | Painting of Ladies Dorm | Ladies Dorm | SPE21-1548-CNPR | Iris J. Sixto | 0 |  | 1 | Orig.: 1.00 gal Rev. 1: 1.00 gal Rev. 2: 1.00 gal | gal | F | Polyurethene,Top Coat,Clear |  | PO Issued (1.00 gal) | 2021-02-02 | SPE-022-2021
2021-02-02 | Manila/Bacolod | Painting of Ladies Dorm | Ladies Dorm | SPE21-1548-CNPR | Iris J. Sixto | 0 |  | 2 | Orig.: 1.00 gls Rev. 1: 1.00 gls Rev. 2: 1.00 gls | gls | F | Acrylic Thinner |  | PO Issued (1.00 gls) | 2021-02-02 | SPE-022-2021
2021-02-02 | Manila/Bacolod | Painting of Ladies Dorm | Ladies Dorm | SPE21-1548-CNPR | Iris J. Sixto | 0 |  | 20 |  | shts | B | Sand Paper,Grit 80 | 02.06.2021 - Delivered DR# 2382-CNPR | Fully Delivered | 2021-02-02 | SPE-022-2021
2021-02-02 | Manila/Bacolod | Painting of Ladies Dorm | Ladies Dorm | SPE21-1548-CNPR | Iris J. Sixto | 0 |  | 30 |  | shts | C | Sand Paper,Grit 120 |  | PO Issued (30.00 shts) | 2021-02-02 | SPE-022-2021
2021-02-02 | Manila/Bacolod | Painting of Ladies Dorm | Ladies Dorm | SPE21-1548-CNPR | Iris J. Sixto | 0 |  | 5 |  | pcs | D | Brush, Paint #2 | 02.06.2021 - Delivered DR# 2380-CNPR | Fully Delivered | 2021-02-02 | SPE-022-2021
2021-02-02 | Manila/Bacolod | Painting of Ladies Dorm | Ladies Dorm | SPE21-1548-CNPR | Iris J. Sixto | 0 |  | 10 |  | pcs | D | Brush,Paint, Roller, Refill,#4 | 02.06.2021 - Delivered DR# 2380-CNPR | Fully Delivered | 2021-02-02 | SPE-022-2021
2021-02-02 | Manila/Bacolod | Painting of Ladies Dorm | Ladies Dorm | SPE21-1548-CNPR | Iris J. Sixto | 0 |  | 5 |  | rolls | F | Masking Tape,3/4 |  | PO Issued (5.00 rolls) | 2021-02-02 | SPE-022-2021
2021-01-14 | Bacolod | For grasscutting at plantsite | For grasscutter use | ENV21-1549-CNPR | Genielyne V. Mondejar | 0 |  | 20 |  | liters | A | Gasoline, Unleaded | 02.05.2021 - Delivered DR# 2398-CNPR | Fully Delivered | 2021-01-22 | HR-019-2021
2021-01-15 | Bacolod | For Grass Cutter | Safety /Admin | HAS21-1550-CNPR | Ricky D. Madeja | 0 |  | 8 |  | liters | B | Unleaded Gasoline | 02.05.2021 - Delivered DR# 2397-CNPR | Fully Delivered | 2021-02-03 | HR-012-2021
2021-01-15 | Bacolod | For Grass Cutter | Safety /Admin | HAS21-1550-CNPR | Ricky D. Madeja | 0 |  | 1 |  | kilo | A | Nylon, no. 300 | 02.06.2021 - Delivered DR# 2399-CNPR | Fully Delivered | 2021-02-03 | HR-012-2021
2021-01-07 | Manila/Bacolod | Double Wall & Ceiling (insulation) | Ladies Dorm | SPE21-1551-CNPR | Iris J. Sixto | 65.5 |  | 3 | Orig.: 3.00 rolls Rev. 1: 3.00 rolls Rev. 2: 3.00 rolls | rolls | A | Tarpfoil double sided aluminum 1m.widthx100mtr long | 02.06.2021 - Delivered DR# 2417-CNPR | Fully Delivered | 2021-02-04 | FR-006-2021
2021-01-07 | Manila/Bacolod | Double Wall & Ceiling (insulation) | Ladies Dorm | SPE21-1551-CNPR | Iris J. Sixto | 19 |  | 20 |  | tubes |  | silicone sealant | For RFQ | Pending | 2021-02-04 | FR-006-2021
2021-01-19 | Manila/Bacolod | Service Entrance for Ladies Dormitory | CENPRI Employees | SPE21-1553-CNPR | Kennah Sasamoto | 0 |  | 2 |  | lengths | A | RSC pipe, 1 1/4" diameter |  | PO Issued (2.00 lengths) | 2021-01-22 | SPE-027-2021
2021-01-19 | Manila/Bacolod | Service Entrance for Ladies Dormitory | CENPRI Employees | SPE21-1553-CNPR | Kennah Sasamoto | 0 |  | 1 |  | piece | A | Service entrance cap, 1 1/4" diameter |  | PO Issued (1.00 piece) | 2021-02-05 | SPE-027-2021
2021-01-19 | Manila/Bacolod | Service Entrance for Ladies Dormitory | CENPRI Employees | SPE21-1553-CNPR | Kennah Sasamoto | 2 |  | 1 |  | piece | A | Grounding rod, 5/8" x 8ft. |  | PO Issued (1.00 piece) | 2021-02-05 | SPE-027-2021
2021-01-19 | Manila/Bacolod | Service Entrance for Ladies Dormitory | CENPRI Employees | SPE21-1553-CNPR | Kennah Sasamoto | 0 |  | 1 |  | piece | A | Solderless split bolt connector, 4 AWG |  | PO Issued (1.00 piece) | 2021-02-05 | SPE-027-2021
2021-01-19 | Manila/Bacolod | Service Entrance for Ladies Dormitory | CENPRI Employees | SPE21-1553-CNPR | Kennah Sasamoto | 0 |  | 1 |  | piece | A | LB condulet, 1 1/4" |  | PO Issued (1.00 piece) | 2021-02-05 | SPE-027-2021
2021-01-19 | Manila/Bacolod | Service Entrance for Ladies Dormitory | CENPRI Employees | SPE21-1553-CNPR | Kennah Sasamoto | 0 |  | 10 |  | pieces. | A | metal clamp, double hole, 1 1/4" |  | PO Issued (10.00 pieces.) | 2021-02-05 | SPE-027-2021
2021-01-19 | Manila/Bacolod | Service Entrance for Ladies Dormitory | CENPRI Employees | SPE21-1553-CNPR | Kennah Sasamoto | 0 |  | 5 |  | mtrs. | A | Mica tube, 10mm |  | PO Issued (5.00 mtrs.) | 2021-02-05 | SPE-027-2021
2021-01-19 | Manila/Bacolod | Service Entrance for Ladies Dormitory | CENPRI Employees | SPE21-1553-CNPR | Kennah Sasamoto | 0 |  | 4 |  | pcs. | A | Conduit connector, rsc, 1 1/4" |  | PO Issued (4.00 pcs.) | 2021-02-05 | SPE-027-2021
2021-01-19 | Manila/Bacolod | Service Entrance for Ladies Dormitory | CENPRI Employees | SPE21-1553-CNPR | Kennah Sasamoto | 0 |  | 5 |  | mtrs. | C | 8mm2 copper wire, THW, green |  | PO Issued (5.00 mtrs.) | 2021-02-05 | SPE-027-2021
2021-01-19 | Manila/Bacolod | Service Entrance for Ladies Dormitory | CENPRI Employees | SPE21-1553-CNPR | Kennah Sasamoto | 0 |  | 20 |  | mtrs. | A | 22mm2 copper wire, THW, black |  | PO Issued (20.00 mtrs.) | 2021-02-05 | SPE-027-2021
2021-02-05 | Manila/Bacolod | Power Supply for Water Pump. | Installation of Pressure Tank at Warehouse Building Water Supply. (Admin) | SPE21-1554-CNPR | Iris J. Sixto | 0 |  | 1 |  | pc | A | Cercuit Breaker Bolt On 30 amps, Single Phase, GE |  | PO Issued (1.00 pc) | 2021-02-05 | SPE-029-2021
2021-02-05 | Manila/Bacolod | Power Supply for Water Pump. | Installation of Pressure Tank at Warehouse Building Water Supply. (Admin) | SPE21-1554-CNPR | Iris J. Sixto | 0 |  | 1 |  | pcs | A | Safety Breaker w/Cover 30 amps |  | PO Issued (1.00 pcs) | 2021-02-05 | SPE-029-2021
2021-02-05 | Manila/Bacolod | Power Supply for Water Pump. | Installation of Pressure Tank at Warehouse Building Water Supply. (Admin) | SPE21-1554-CNPR | Iris J. Sixto | 35 |  | 20 |  | pcs | A | Pvc Clamp 1/2" orange |  | PO Issued (20.00 pcs) | 2021-02-05 | SPE-029-2021
2021-02-05 | Manila/Bacolod | Power Supply for Water Pump. | Installation of Pressure Tank at Warehouse Building Water Supply. (Admin) | SPE21-1554-CNPR | Iris J. Sixto | 0 |  | 10 |  | pcs | C | Screw w/tox 1/8" |  | PO Issued (10.00 pcs) | 2021-02-05 | SPE-029-2021
2021-02-05 | Manila/Bacolod | Power Supply for Water Pump. | Installation of Pressure Tank at Warehouse Building Water Supply. (Admin) | SPE21-1554-CNPR | Iris J. Sixto | 23 |  | 15 |  | length | A | Electrical Conduit Pipe 1/2 Pvc orange. |  | PO Issued (15.00 length) | 2021-02-05 | SPE-029-2021
2021-02-05 | Manila/Bacolod | Power Supply for Water Pump. | Installation of Pressure Tank at Warehouse Building Water Supply. (Admin) | SPE21-1554-CNPR | Iris J. Sixto | 19 |  | 1 |  | roll | B | Electrical Tape Big. |  |  | 2021-02-05 | SPE-029-2021
2021-01-20 | Manila/Bacolod | Service Entrance for CENPRI Canteen Electrical CENECO Requirements | CENPRI Employees | EIC21-1555-CNPR | Iris Sixto / Kennah Sasamoto | 0 |  | 1 | Orig.: 1.00 length | length | A | RSC pipe, 1" diameter |  | PO Issued (1.00 length) | 2021-01-23 | EIC-031-2021
2021-01-20 | Manila/Bacolod | Service Entrance for CENPRI Canteen Electrical CENECO Requirements | CENPRI Employees | EIC21-1555-CNPR | Iris Sixto / Kennah Sasamoto | 0 |  | 1 | Orig.: 1.00 pc. | pc. | A | Service entrance cap, 1" |  | PO Issued (1.00 pc.) | 2021-02-05 | EIC-031-2021
2021-01-20 | Manila/Bacolod | Service Entrance for CENPRI Canteen Electrical CENECO Requirements | CENPRI Employees | EIC21-1555-CNPR | Iris Sixto / Kennah Sasamoto | 0 |  | 5 |  | mtrs. | A | Mica tube, 8mm |  | PO Issued (5.00 mtrs.) | 2021-02-05 | EIC-031-2021
2021-01-20 | Manila/Bacolod | Service Entrance for CENPRI Canteen Electrical CENECO Requirements | CENPRI Employees | EIC21-1555-CNPR | Iris Sixto / Kennah Sasamoto | 3 |  | 1 | Orig.: 1.00 pc. | pc. | A | LB condulet, 1" |  | PO Issued (1.00 pc.) | 2021-02-05 | EIC-031-2021
2021-01-20 | Manila/Bacolod | Service Entrance for CENPRI Canteen Electrical CENECO Requirements | CENPRI Employees | EIC21-1555-CNPR | Iris Sixto / Kennah Sasamoto | 2 |  | 1 |  | pc. | A | Grounding rod, 5/8" x 8ft |  | PO Issued (1.00 pc.) | 2021-02-05 | EIC-031-2021
2021-01-20 | Manila/Bacolod | Service Entrance for CENPRI Canteen Electrical CENECO Requirements | CENPRI Employees | EIC21-1555-CNPR | Iris Sixto / Kennah Sasamoto | 0 |  | 5 |  | pcs. | A | metal clamp, double hole, 1" |  | PO Issued (5.00 pcs.) | 2021-02-05 | EIC-031-2021
2021-01-20 | Manila/Bacolod | Service Entrance for CENPRI Canteen Electrical CENECO Requirements | CENPRI Employees | EIC21-1555-CNPR | Iris Sixto / Kennah Sasamoto | 0 |  | 1 |  | pc. | A | Solderless split bolt connector, 14 AWG |  | PO Issued (1.00 pc.) | 2021-02-05 | EIC-031-2021
2021-01-20 | Manila/Bacolod | Service Entrance for CENPRI Canteen Electrical CENECO Requirements | CENPRI Employees | EIC21-1555-CNPR | Iris Sixto / Kennah Sasamoto | 61 |  | 1 |  | pc. | A | Conduit connector, rsc, 1" |  | PO Issued (1.00 pc.) | 2021-02-05 | EIC-031-2021
2021-01-20 | Manila/Bacolod | Service Entrance for CENPRI Canteen Electrical CENECO Requirements | CENPRI Employees | EIC21-1555-CNPR | Iris Sixto / Kennah Sasamoto | 0 |  | 5 |  | mtrs. | A | 5.5mm2 copper wire, THW, green |  | PO Issued (5.00 mtrs.) | 2021-02-05 | EIC-031-2021
2021-01-20 | Manila/Bacolod | Service Entrance for CENPRI Canteen Electrical CENECO Requirements | CENPRI Employees | EIC21-1555-CNPR | Iris Sixto / Kennah Sasamoto | 0 |  | 20 |  | mtrs. | A | 8mm2 copper wire, THW, black |  | PO Issued (20.00 mtrs.) | 2021-02-05 | EIC-031-2021
2021-01-22 | Manila/Bacolod | Repair of Comfort Rooms at ECMG Office and Site Staffhaus | Admin | SPE21-1557-CNPR | Iris J. Sixto | 3 |  | 8 |  | pcs | A | Angle Valve,1/2"x1/2" |  | PO Issued (8.00 pcs) | 2021-02-08 | SPE-028-2021
2021-01-22 | Manila/Bacolod | Repair of Comfort Rooms at ECMG Office and Site Staffhaus | Admin | SPE21-1557-CNPR | Iris J. Sixto | 0 |  | 4 |  | pcs | A | Lavatory Faucet |  | PO Issued (4.00 pcs) | 2021-02-08 | SPE-028-2021
2021-01-22 | Manila/Bacolod | Repair of Comfort Rooms at ECMG Office and Site Staffhaus | Admin | SPE21-1557-CNPR | Iris J. Sixto | 0 |  | 4 |  | sets | A | Lavatory, P-trap 1-1/4" |  | PO Issued (4.00 sets) | 2021-02-08 | SPE-028-2021
2021-01-22 | Manila/Bacolod | Repair of Comfort Rooms at ECMG Office and Site Staffhaus | Admin | SPE21-1557-CNPR | Iris J. Sixto | 5 |  | 3 |  | pcs | A | Water Faucets 1/2" |  | PO Issued (3.00 pcs) | 2021-02-08 | SPE-028-2021
2021-01-22 | Manila/Bacolod | Repair of Comfort Rooms at ECMG Office and Site Staffhaus | Admin | SPE21-1557-CNPR | Iris J. Sixto | 2 |  | 8 |  | pcs | A | LED bulb 14 watts |  | PO Issued (8.00 pcs) | 2021-02-08 | SPE-028-2021
2021-01-22 | Manila/Bacolod | Repair of Comfort Rooms at ECMG Office and Site Staffhaus | Admin | SPE21-1557-CNPR | Iris J. Sixto | 0 |  | 2 |  | pcs | A | Receptacle Rubberized |  | PO Issued (2.00 pcs) | 2021-02-08 | SPE-028-2021
2021-01-22 | Manila/Bacolod | Repair of Comfort Rooms at ECMG Office and Site Staffhaus | Admin | SPE21-1557-CNPR | Iris J. Sixto | 0 |  | 8 |  | pcs | A | Flexible Hose 1/2"x1/2"x18" |  | PO Issued (8.00 pcs) | 2021-02-08 | SPE-028-2021
2021-01-22 | Manila/Bacolod | Repair of Comfort Rooms at ECMG Office and Site Staffhaus | Admin | SPE21-1557-CNPR | Iris J. Sixto | 0 |  | 8 |  | pcs | A | Toilet Bowl FlapValve (rubber) |  | PO Issued (8.00 pcs) | 2021-02-08 | SPE-028-2021
2021-01-22 | Manila/Bacolod | Repair of Comfort Rooms at ECMG Office and Site Staffhaus | Admin | SPE21-1557-CNPR | Iris J. Sixto | 1 |  | 1 |  | pc | A | Flush Door 70cmx210cm |  | PO Issued (1.00 pc) | 2021-02-08 | SPE-028-2021
2021-01-22 | Manila/Bacolod | Repair of Comfort Rooms at ECMG Office and Site Staffhaus | Admin | SPE21-1557-CNPR | Iris J. Sixto | 0 |  | 1 |  | sets | A | Door Jamb, 70cmx210cmx4" |  | PO Issued (1.00 sets) | 2021-02-08 | SPE-028-2021
2021-01-22 | Manila/Bacolod | Repair of Comfort Rooms at ECMG Office and Site Staffhaus | Admin | SPE21-1557-CNPR | Iris J. Sixto | 0 |  | 2 | Orig.: 2.00 sets | sets | A | Henges 4"x4" heavy duty |  | PO Issued (2.00 sets) | 2021-02-08 | SPE-028-2021
2021-01-22 | Manila/Bacolod | Repair of Comfort Rooms at ECMG Office and Site Staffhaus | Admin | SPE21-1557-CNPR | Iris J. Sixto | 0 |  | 1 |  | set | A | Door Knob |  | PO Issued (1.00 set) | 2021-02-08 | SPE-028-2021
2021-01-22 | Manila/Bacolod | Repair of Comfort Rooms at ECMG Office and Site Staffhaus | Admin | SPE21-1557-CNPR | Iris J. Sixto | 0 |  | 24 |  | pcs | A | Corner Bracket,2"x2" |  | PO Issued (24.00 pcs) | 2021-02-08 | SPE-028-2021
2021-01-22 | Manila/Bacolod | Repair of Comfort Rooms at ECMG Office and Site Staffhaus | Admin | SPE21-1557-CNPR | Iris J. Sixto | 0 |  | 5 |  | pcs | A | Toilet Bowl Flash Handle/ Lever |  | PO Issued (5.00 pcs) | 2021-02-08 | SPE-028-2021
2021-01-22 | Manila/Bacolod | Repair of Comfort Rooms at ECMG Office and Site Staffhaus | Admin | SPE21-1557-CNPR | Iris J. Sixto | 0 |  | 96 | Orig.: 96.00 pcs | pcs | A | Screww/Tox 3/16" |  | PO Issued (96.00 pcs) | 2021-02-08 | SPE-028-2021
2021-01-22 | Manila/Bacolod | Repair of Comfort Rooms at ECMG Office and Site Staffhaus | Admin | SPE21-1557-CNPR | Iris J. Sixto | 7 |  | 5 |  | rolls | A | Tapelone,3/4 |  | PO Issued (5.00 rolls) | 2021-02-08 | SPE-028-2021
2021-01-22 | Manila/Bacolod | Repair of Comfort Rooms at ECMG Office and Site Staffhaus | Admin | SPE21-1557-CNPR | Iris J. Sixto | 0 |  | 3 |  | pcs | B | Urinal Faucet | For RFQ | Pending | 2021-02-08 | SPE-028-2021
2021-01-09 |  | Operations and Maintenance Consumables | Running Units (Units 1-5) | OPE21-1558-CNPR | Alona T. Arroyo | 0 |  | 5 |  | pcs | A | Disc, Grinding, 4" x 1/4" x 5/8, (Tyrolit 27 A30Q-BF) |  | PO Issued (5.00 pcs) | 2021-02-08 | PR-008-2021